## Draft Gantt
Parking Buddy — Draft Gantt Chart
Change the blue dates and the chart updates. Click the chart border, Ctrl+C, then paste into Word.
Task | Start Date | Duration (days) | End Date
1.1 Project Management | 2026-08-03 | 138 | 2026-12-18
1.2 Requirements and Analysis | 2026-08-10 | 26 | 2026-09-04
1.3 UX/UI Design | 2026-09-08 | 39 | 2026-10-16
1.4 System Architecture and Setup | 2026-09-08 | 18 | 2026-09-25
1.5 Backend and Integrations | 2026-09-28 | 40 | 2026-11-06
1.6 Driver App Development (Mobile and Web) | 2026-10-19 | 38 | 2026-11-25
1.7 Operator Dashboard and Admin | 2026-10-19 | 38 | 2026-11-25
1.8 Testing and Quality Assurance | 2026-10-19 | 54 | 2026-12-11
1.9 Deployment and Launch | 2026-12-07 | 11 | 2026-12-17